## Sheet1
DESCRIPTION | EVALUATION | RESPONSIBILITY | LIKELIHOOD | IMPACT | CONTROLS | RESPONSE
Crash of the database | This is key to the operation of the service, since all information are stored in the database | The IT department should prevent this from happening | Not likely | Severe. Data will be lost | Create redundance server | Quickly switch to backup server
Hacking of the website | This implies handing over of all information to criminal | As developer one you provide robust check that only the right people have access to the database | Not likely | Severe. Stolen data can be used by hackers for different purposes | make sure submitted forms are validated and with hidden tags. | The Database server should be lockdown immediately to reduce the cost of damage and the website taking down completely until the site is full recovered from the hackers
Issues with hosting site | If the hosting site is down that implies the URI can't be reach | The hosting site show have an alternative to reducing the downtime to a minimal and also be able to re-dirct traffic | Not likely | No too severe if the downtime is brought to a minimal | Have an alternative hosting site as plan B | If downtime is beyound acceptable values then switch to alternative hosting sites
sudden surge in traffic | This is likely to be when more people search for their registered moodle at the same time | IT department | likely | Severe. Crash the Database | vartical scalability | Increase processor power
surge in weather temperature | In summer and with clobal warming higher temperature can persist a little longer than expected. | IT department | not likely | Severe Crash the Database | Have cooling systems in place | turn cooling system on
No sign in page was created | the implies have accesss to someone's id number, you can access the service | There is the need to create a login page | most likely | Data of user can be stolen which is very severe | creation of a login page will be intoduce at a letter stage | disable user who's ID has been compromised.